## Sheet1
Iteration Name | Name of the Feature | Projected Hours | Commited Hours
Iteration-1 | to-do | 2 day | 3 day
Iteration-1 | Basic cal | 3 day | 48 mint
Iteration-1 | Dashboard | 2 day | 2 day
Iteration-1 | Unit testing | 2 days | 2.5 days
|  | 72 Hours | 60.8 Hours
Iteration-2 | useful link | 2 days | 1.5 days
Iteration-2 | calendar task show | 2 days | 2 days
Iteration-2 | basic time est | 3 day | 1.5 day
Iteration-2 | Unit testing | 1 days | 1 days
Iteration-2 | Integration test | 2 days | 2 days
|  | 80 Hours | 64 Hours
| Reminder | 1 days | 2 days
Iteration-3 | Tutorial | 2 days | 2 days
Iteration-3 | Interactive calendar | 3 days | 4 days
Iteration-3 | Unit testing | 1.5 days | 1 days
Iteration-3 | Integration test | 1 days | 1 days
Iteration-3 | Acceptance test | 0.5 days | 0.5 days
| Check deleted task | 3 days | 2.5 days
| time estimato | 3 days | 1 days
|  | 15 days | 15 days
|  | 120 Hours | 120 Hours
| Time Estimated | Time Spent
Iteration-1 | 72 | 60.8
Iteration-2 | 80 | 64
Iteration-3 | 120 | 120